## Sheet1
| Project Name | Project Duration | Project start date | Project end date
| Quiz - Team 4 | 106 | 2017-11-06 | 2018-02-20
Task ID | Task Description | Assigned to | Task Duration | Start Date | End Date | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16 | 2017-12-17 | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-23 | 2017-12-24 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29 | 2017-12-30 | 2017-12-31 | 2018-01-01 | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-06 | 2018-01-07 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-13 | 2018-01-14 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | 2018-01-20 | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-27 | 2018-01-28 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21
1 | Design Phase 1
1.1 | Functional Requirements |  | 11 | 2017-11-06 | 2017-11-16 | X | X | X | X | X | X | X | X | X | X | X
1.1.1 | Draft functional requirements | Ryan Harris | 5 | 2017-11-06 | 2017-11-10 | X | X | X | X | X
1.1.2 | Acceptance Criteria for each requirement | Ryan Harris | 5 | 2017-11-11 | 2017-11-15 | [5 empty] | X | X | X | X | X
1.1.3 | Catergorize each requirement into MoSCoW notation | Whole Team | 1 | 2017-11-16 | 2017-11-16 | [10 empty] | X
1.2 | Non-Functional Requirements |  | 13 | 2017-11-17 | 2017-11-27 | [11 empty] | X | X | X | X | X | X | X | X | X | X | X
1.2.1 | Draft Non-functional requirements | Rayner Da Cruz | 4 | 2017-11-17 | 2017-11-20 | [11 empty] | X | X | X | X
1.2.2 | Acceptance Criteria for each requirement | Rayner Da Cruz | 3 | 2017-11-21 | 2017-11-23 | [15 empty] | X | X | X
1.2.3 | Catergorize each requirement into MoSCoW notation | Whole Team | 1 | 2017-11-23 | 2017-11-23 | [17 empty] | X
1.3 | Use Case Diagram | Spyros Lontos | 5 | 2017-11-23 | 2017-11-27 | [17 empty] | X | X | X | X | X
1.4 | Use Case Descriptions: |  | 7 | 2017-11-28 | 2017-12-04 | [22 empty] | X | X | X | X | X | X | X
1.4.1 | Setup Quiz | Reem Alotaibi | 2 | 2017-11-28 | 2017-11-29 | [22 empty] | X | X
1.4.2 | Take Quiz | Alfie Potter | 2 | 2017-11-30 | 2017-12-01 | [24 empty] | X | X
1.4.3 | Obtain Statistics | Adriano Sole | 2 | 2017-12-02 | 2017-12-03 | [26 empty] | X | X
1.4.4 | Modify Questions | Spyros Lontos | 1 | 2017-12-04 | 2017-12-04 | [28 empty] | X
1.5 | Milestone: Review Before submission | Whole Team | 2 | 2017-12-04 | 2017-12-05 | [28 empty] | X | X
Christmas Break and Exam Period
| Christmas Break and Exam Period |  | 50 | 2017-12-08 | 2018-01-26 | [32 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
2 | Design Phase 2
2.1 | Detailed Use Case Descriptions |  | 6 | 2018-01-29 | 2018-02-03 | [84 empty] | X | X | X | X | X | X
2.1.1 | Detailed Use Case 1 - Basic & Alternate flow, Pre & Post conditions | Whole Team | 3 | 2018-01-29 | 2018-01-31 | [84 empty] | X | X | X
2.1.2 | Detailed Use Case 2 - Basic & Alternate flow, Pre & Post conditions | Whole Team | 3 | 2018-02-01 | 2018-02-03 | [87 empty] | X | X | X
2.2 | UML Class Diagram |  | 5 | 2018-02-04 | 2018-02-13 | [90 empty] | X | X | X | X | X | X | X | X | X | X
2.2.1 | Design UML Class Diagram using the Use Cases as the basis | Spyros Lontos | 5 | 2018-02-04 | 2018-02-08 | [90 empty] | X | X | X | X | X
2.2.1 | Class Diagram descriptions | Spyros Lontos | 5 | 2018-02-09 | 2018-02-13 | [95 empty] | X | X | X | X | X
2.3 | Project Plan |  | 1 | 2018-02-14 | 2018-02-16 | [100 empty] | X | X | X
2.3.1 | Design gantt chart with formulas | Rayner Da Cruz | 1 | 2018-02-14 | 2018-02-14 | [100 empty] | X
2.3.2 | Fill in dates and timings for the project | Adriano Sole | 2 | 2018-02-15 | 2018-02-16 | [101 empty] | X | X
2.4 | Risk Assessment | Alfie Potter | 4 | 2018-02-15 | 2018-02-18 | [101 empty] | X | X | X | X
2.5 | Milestone: Review Before submission | Whole Team | 2 | 2018-02-19 | 2018-02-20 | [105 empty] | X | X
Formulas:
Project end date = MIN([Project end date, row below]:E10)